## GanttChart
McGill Data Science Capstone Project
Keras the Python
Objectives |  | 2019-01-01 | [20 empty] | 2019-02-01 | [27 empty] | 2019-03-01
A | Class Presentation 1 | Week2 | [6 empty] | Week3 | [6 empty] | Week4 | [6 empty] | Week1 | [6 empty] | Week2 | [6 empty] | Week3 | [6 empty] | Week4 | [6 empty] | Week1 | [6 empty] | Week2
|  | Sun | Mon | Tues | Wed | Thurs | Fri | Sat | Sun | Mon | Tues | Wed | Thurs | Fri | Sat | Sun | Mon | Tues | Wed | Thu | Fr | Sat | Sun | Mon | Tues | Wed | Thurs | Fri | Sat | Sun | Mon | Tues | Wed | Thurs | Fri | Sat | Sun | Mon | Tues | Wed | Thu | Fr | Sat | Sun | Mon | Tues | Wed | Thurs | Fri | Sat | Sun | Mon | Tues | Wed | Thurs | Fri | Sat | Sun | Mon | Tues | Wed | Thurs | Fri | Sat
1 | Choose data sets to work with - All
2 | Import Datasets - All
3 | Iniital Analysis-All
4 | Literature Review- All
5 | Create Template - Mustafizur
6 | Literature Review- Razvan
7 | Produce Graphs - Tashlin
B | Class Presentation 2
1 | Process Datasets - All
2 | Produce population density vs incident graph - Jun
3 | Produce Correlations graph - Tashlin
4 | Research on prediction models - Razvan
5 | Create Presentation Template and add literature - Mustafizur
C | Class Presentation 3
1 | Merge weather dataset with fire department's-Jun
2 | Generalize census data for each year - Obaro
3 | Discuss which predictive model to implement - All
4 | Implement Decision Tree model with XGBoost on dataset - All
5 | Try Time Series Keras examples from the internet - All
6 | Try FB Prophet example with time series data - All
D | Final Report
1 | Create Template - Mustafizur
2 | Provide Literature Review Reference Links - Razvan
3 | Collect Reference LInks (webpages, articles) - All
4 | Edit the final report - All
Completed
Projected
Meetings on subject